## Blad1
Master's thesis
Willy Själin
# | Activity | Dependencies | Week
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14* | 15 | 16 | 17 | 18 | 19 | 20
A1 | Understand the Eiffel-framework | bar: Week 1 to Week 3
A2 | Understand the Eiffel-event generating script | A1 | bar: Week 2 to Week 3
A3 | Make eventual changes to the script | A2 | bar: Week 3 to Week 4
A4 | Generate data that the model will use | A3 | bar: Week 4 to Week 5
A5 | Set up AI-models (ink. Understanding/tweaking) | A4 | bar: Week 5 to Week 6
A6 | Train model | A5 | bar: Week 7
M1 | Milestone 1 (Peer Review 1) | bar: Week 8
A7 | Literature study/ find relating work | bar: Week 4 to Week 9
A8 | Evaluate the model | A6 | bar: Week 9 to Week 10
R1 | Write Introduction, part of method and part of background regarding Eiffel. | A1 | bar: Week 2 to Week 7
R2 | Write Background parts of the evaluation/results | A1, A7 | bar: Week 8 to Week 13
M2 | Milestone 2 (Peer Review 2) | M1 | bar: Week 14*
R3 | Finalize the report and write discussion and conclusion | R2 | bar: Week 14* to Week 19
R4 | Proofread and finalize the unfinished parts. | R3 | bar: Week 19
M3 | Milestone 3 (Finish submission) | M2 | bar: Week 20
PD1 | Write project diary
Comments:
*Easter holiday
Red indicates the weeks of milestones and or deadlines.